## Main
ItemId | Item Name | Description | Project | Sprint | Assignee | Created by | Status | Priority | Created On | Estimation Points | Start Date | End Date | Completed On | Epic | Tags | Release | Item Type | ParentId | Sprint Type | Comment
SP-I77 | Not able to switch to normal view. |  | Sample Project | Backlog | Jonus | Jonus | To do | Low | 22/Jun/2020 01:25 PM | 5 | 2021-04-01 01:00 | 2021-05-10 18:00 |  | On boarding |  | IVM 2.0 | Task |  | Backlog
SP-I76 | 3D view is not working |  | Sample Project | Backlog | Jonus | Jonus | To do | Medium | 22/Jun/2020 01:25 PM | 8 | 2021-08-13 01:00 | 2021-08-30 18:00 |  | On boarding |  | IVM 2.0 | Bug | SP-I77 | Backlog
SP-I75 | On click of 'Switch to normal mode' take the user back to the normal view |  | Sample Project | Backlog | Jonus | Jonus | To do | Medium | 22/Jun/2020 01:25 PM | 3 |  |  |  | On boarding |  | IVM 2.0 | Task |  | Backlog
SP-I74 | Zoom in and zoom out features. |  | Sample Project | Backlog | Jonus | Jonus | To do | Medium | 22/Jun/2020 01:25 PM | 1 | 2021-08-13 01:00 | 2021-08-30 18:00 |  | On boarding |  | IVM 2.0 | Bug |  | Backlog
SP-I73 | Insert a 3D view option only for all the items in the user's bag. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | Low | 22/Jun/2020 01:25 PM | 2 | 2019-08-14 01:00 | 2021-08-30 18:00 | 14/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I72 | As a user, I would like to have a 3D view of all the appliances. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | High | 22/Jun/2020 01:25 PM | 0 | 2019-08-16 01:00 | 2019-09-20 18:00 | 13/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I71 | Item not saved in favorites after marking it as favorite |  | Sample Project | User interface sprint | Jonus | Jonus | Done | High | 22/Jun/2020 01:25 PM | 8 | 2019-08-15 01:00 | 2019-09-20 18:00 | 12/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I70 | Favorites icon missing |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 0 | 2019-08-14 01:00 | 2019-09-20 18:00 | 11/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I69 | As a user, I would like to receive weekly mails on the latest appliances on your site. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | High | 22/Jun/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-09-20 18:00 | 10/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I68 | On click of favorite, store the categories in particular user folder. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | Low | 22/Jun/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 | 09/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I67 | Create a favorite button or icon for every category. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 | 08/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I66 | Create a folder for favorites section user-wise. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | Medium | 22/Jun/2020 01:25 PM | 8 |  |  | 07/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I65 | As a user, I would like to have a favorites sections where I can save all my favorite categories in it. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | Low | 22/Jun/2020 01:25 PM | 2 | 2019-08-13 01:00 | 2019-08-30 18:00 | 06/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I64 | Data not fetched after filter. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 1 | 2019-08-14 01:00 | 2019-08-30 18:00 | 30/Jun/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I63 | List down all the selection criterias and create the filter icon |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 3 | 2019-08-16 01:00 | 2019-09-20 18:00 | 05/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I62 | Create a folder for category and list all the items in it. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 5 | 2019-08-15 01:00 | 2019-09-20 18:00 | 04/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I61 | As a user, I would like to filter the appliances based on the criterias |  | Sample Project | User interface sprint | Jonus | Jonus | Done | None | 22/Jun/2020 01:25 PM | 1 | 2019-08-14 01:00 | 2019-09-20 18:00 | 03/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I60 | Create a rating feature after the user purchases the items in the bag. |  | Sample Project | User interface sprint | Jonus | Jonus | Done | High | 22/Jun/2020 01:25 PM | 8 | 2019-08-13 01:00 | 2019-09-20 18:00 | 01/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I59 | I cannot enter my card name. Field is not accepting letters. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | High | 11/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 | 28/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I58 | Create a section and pull payment details from the user's history. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 0 | 2019-08-13 01:00 | 2019-08-30 18:00 | 27/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I57 | As a user, I'd like to see all the payment history in my profile. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Low | 11/Jul/2020 01:25 PM | 5 |  |  | 26/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I56 | Delay in receiving the query. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | None | 11/Jul/2020 01:25 PM | 0 | 2019-08-13 01:00 | 2019-08-30 18:00 | 25/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I55 | When a user submits a query, report the ticket to the support via email and chat. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | None | 11/Jul/2020 01:25 PM | 3 | 2019-08-14 01:00 | 2019-08-30 18:00 | 22/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I54 | Need Help? Chat option. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Low | 11/Jul/2020 01:25 PM | 3 | 2019-08-16 01:00 | 2019-09-20 18:00 | 21/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I53 | As a user, I need a complaint box if the purchased items are yet to be dispatched. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 2 | 2019-08-15 01:00 | 2019-09-20 18:00 | 20/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I52 | Start Your Purchase button is missing. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | High | 11/Jul/2020 01:25 PM | 5 | 2019-08-14 01:00 | 2019-09-20 18:00 | 19/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I51 | Items are not stored when user clicks 'Move to Bag' button. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Low | 11/Jul/2020 01:25 PM | 2 | 2019-08-13 01:00 | 2019-09-20 18:00 | 18/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I50 | If 'Move to Bag' is clicked, push the items to the 'My Bag' folder of the particular user. And, store all the items to the dispatched in our database. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 8 | 2019-08-13 01:00 | 2019-08-30 18:00 | 17/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I49 | In empty 'My Bag' folder insert a button 'Start Your Purchase'. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Low | 11/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 | 16/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I48 | Place two buttons 'Add to Wishlist' and 'Move to Bag' for all the items. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 5 |  |  | 23/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I47 | Design the 'My bag' icon for every profile |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Low | 11/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 | 22/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I46 | As a user, I prefer to have 'my bag' folder that will have all the items that I would like to buy. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | None | 11/Jul/2020 01:25 PM | 3 | 2019-08-14 01:00 | 2019-08-30 18:00 | 21/Jul/2020 12:00 AM |  |  |  | Task |  | Completed
SP-I45 | Wishlist is not loading |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | None | 11/Jul/2020 01:25 PM | 1 | 2019-08-16 01:00 | 2019-09-20 18:00 | 20/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I44 | On click of whislist, save the respective items to the user's whislist. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | None | 11/Jul/2020 01:25 PM | 0 | 2019-08-15 01:00 | 2019-09-20 18:00 | 19/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I43 | Create an icon for whislist |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 2 | 2019-08-14 01:00 | 2019-09-20 18:00 | 18/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I42 | As a user, I would like to have a whislist icon. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-09-20 18:00 | 17/Jul/2020 12:00 AM |  |  |  | Story |  | Completed
SP-I41 | Create an 'Add to bag' button in every whislist. |  | Sample Project | Shopping cart sprint | Jonus | Jonus | Done | Medium | 11/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 | 15/Jul/2020 12:00 AM |  |  |  | Bug |  | Completed
SP-I40 | Trigger emails to active users |  | Sample Project | Marketing | Jonus | Jonus | To do | Medium | 23/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 | 23/Jul/2020 12:00 AM | Web Architecture |  | IoT | Bug |  | Future
SP-I39 | Content for the emails |  | Sample Project | Marketing | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 0 |  |  |  | Web Architecture |  | IoT | Task |  | Future
SP-I38 | Promote on social media |  | Sample Project | Marketing | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | Web Architecture |  | IoT | Story |  | Future
SP-I37 | As a user, I would like to read some blogs and tips on buying appliances. |  | Sample Project | Marketing | Martha | Jonus | To do | Low | 26/Jul/2020 01:25 PM | 2 | 2019-08-14 01:00 | 2019-08-30 18:00 |  | Web Architecture |  | IoT | Story |  | Future
SP-I36 | As a user, I need a complaint box if the purchased items are yet to be dispatched. |  | Sample Project | Payments | Martha | Jonus | In progress | Medium | 19/Jul/2020 01:25 PM | 2 | 2019-08-16 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I35 | Start Your Purchase button is missing. |  | Sample Project | Payments | Martha | Jonus | Done | Medium | 18/Jul/2020 01:25 PM | 5 | 2019-08-15 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I34 | Payment mode link is breaking. Check |  | Sample Project | Payments | Martha | Jonus | Done | High | 19/Jul/2020 01:25 PM | 2 | 2019-08-14 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I33 | We cannot track the payment history. |  | Sample Project | Payments | Martha | Jonus | Done | None | 23/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I32 | I don't see the Pay Now button in my bag. |  | Sample Project | Payments | Jonus | Jonus | In progress | Medium | 22/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I31 | Create a rating feature after the user purchases the items in the bag. |  | Sample Project | Payments | Jonus | Jonus | In progress | Medium | 22/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I30 | I cannot enter my card name. Field is not accepting letters. |  | Sample Project | Payments | Jonus | Jonus | In progress | Medium | 18/Jul/2020 01:25 PM | 5 |  |  |  | On boarding |  | IoT | Bug |  | Active
SP-I29 | Create a section and pull payment details from the user's history. |  | Sample Project | Payments | Martha | Jonus | In progress | Medium | 18/Jul/2020 01:25 PM | 2 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I28 | As a user, I'd like to see all the last payment history in my profile. |  | Sample Project | Payments | Martha | Jonus | In progress | Medium | 18/Jul/2020 01:25 PM | 3 | 2019-08-14 01:00 | 2019-08-30 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I27 | Create five themes for payment section. |  | Sample Project | Payments | Martha | Jonus | In progress | None | 20/Jul/2020 01:25 PM | 3 | 2019-08-16 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Task |  | Active
SP-I26 | Access denied for payment page. Check |  | Sample Project | Payments | Martha | Jonus | In progress | Low | 18/Jul/2020 01:25 PM | 2 | 2019-08-15 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Bug |  | Active
SP-I25 | Design icons for the payment module. |  | Sample Project | Payments | Martha | Jonus | To do | Low | 20/Jul/2020 01:25 PM | 5 | 2019-08-14 01:00 | 2019-09-20 18:00 |  | On boarding |  | IoT | Task |  | Active
SP-I24 | Create a new design for the payment page. |  | Sample Project | Payments | Martha | Jonus | In progress | Low | 19/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-09-20 18:00 |  | On boarding |  | IVM 2.0 | Task |  | Active
SP-I23 | As a user, I want an attractive payment page. |  | Sample Project | Payments | Martha | Jonus | Done | Low | 19/Jul/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IVM 2.0 | Task |  | Active
SP-I22 | Seasonal offers are not included after the payment. |  | Sample Project | Payments | Martha | Jonus | To do | Low | 18/Jul/2020 01:25 PM | 8 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IVM 2.0 | Story |  | Active
SP-I21 | I cannot enter the credit card details. |  | Sample Project | Payments | Martha | Jonus | In progress | Medium | 17/Jul/2020 01:25 PM | 1 |  |  |  | On boarding |  | IVM 2.0 | Bug |  | Active
SP-I20 | Default payment modes can only be accessed by premium users. |  | Sample Project | Payments | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | IVM 2.0 | Bug |  | Active
SP-I19 | Create a section to make the payment modes default. |  | Sample Project | Payments | Martha | Jonus | To do | Low | 26/Jul/2020 01:25 PM | 5 | 2019-08-14 01:00 | 2019-08-30 18:00 |  | On boarding |  | IVM 2.0 | Story |  | Active
SP-I18 | As a user, I would like to have only net banking as my payment mode by default. |  | Sample Project | Payments | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 3 | 2019-08-16 01:00 | 2019-09-20 18:00 |  | Web Architecture |  | Beta Release | Task |  | Active
SP-I17 | Couldn't track order. |  | Sample Project | Payments | Martha | Jonus | To do | Low | 26/Jul/2020 01:25 PM | 3 | 2019-08-15 01:00 | 2019-09-20 18:00 |  | Web Architecture |  | Beta Release | Task |  | Active
SP-I16 | Pay Now functionality not working |  | Sample Project | Payments | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 2 | 2019-08-14 01:00 | 2019-09-20 18:00 |  | Web Architecture |  | Beta Release | Task |  | Active
SP-I15 | Click 'Pay Now' place an order on the database and move it to delivery site. |  | Sample Project | Payments | Jonus | Jonus | To do | None | 09/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-09-20 18:00 |  | Web Architecture |  | Beta Release | Bug |  | Active
SP-I13 | Create an 'Order Now' button for all the items in the bag. |  | Sample Project | Payments | Martha | Jonus | To do | Low | 27/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | Web Architecture |  | Beta Release | Task |  | Active
SP-I14 | On click, take the user to a secure payment gateway. Check the card details of the user. |  | Sample Project | Payments | Martha | Jonus | To do | Medium | 26/Jul/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | Web Architecture |  | Beta Release | Bug |  | Active
SP-I12 | Create a 'Add to bag' button in every whislist. |  | Sample Project | Payments | Martha | Jonus | To do | None | 26/Jul/2020 01:25 PM | 3 |  |  |  | Web Architecture |  | Beta Release | Task |  | Active
SP-I11 | As a user, I would like to have an easy payment gateway. |  | Sample Project | Payments | Jonus | Jonus | To do | None | 30/May/2020 01:25 PM | 8 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | Web Architecture |  | Beta Release | Story |  | Active
SP-I10 | Like option is not working |  | Sample Project | Backlog | Martha | Jonus | To do | Medium | 24/Jul/2020 01:25 PM | 5 | 2019-08-14 01:00 | 2019-08-30 18:00 |  | On boarding |  | IVM 2.0 | Bug |  | Backlog
SP-I9 | As a user, I would like to receive weekly mails on the latest appliances on your site. |  | Sample Project | Backlog | Martha | Jonus | To do | Low | 23/Jul/2020 01:25 PM | 3 | 2019-08-16 01:00 | 2019-09-20 18:00 |  | On boarding |  | IVM 2.0 | Story |  | Backlog
SP-I8 | Shop Now' button. |  | Sample Project | Backlog | Martha | Jonus | To do | None | 27/Jul/2020 01:25 PM | 1 | 2019-08-15 01:00 | 2019-09-20 18:00 |  | On boarding |  | IVM 2.0 | Bug |  | Backlog | [{"Comments":"@Frank check this issue and fix ASAP in next sprint","addedBy":"Jonus"}]
SP-I7 | Insert like and dislike icons for all the items. |  | Sample Project | Backlog | Martha | Jonus | To do | Medium | 18/Jul/2020 01:25 PM | 3 | 2019-08-14 01:00 | 2019-09-20 18:00 |  | On boarding |  | Beta Release | Task |  | Backlog | [{"Comments":"I think it is not needed now.","addedBy":"ZohoSprints"},{"Comments":"Anyways, we need to implement this before external release. I will move this to low priority","addedBy":"Jonus"}]
SP-I6 | Generate ideas for the video. |  | Sample Project | Backlog | Martha | Jonus | To do | High | 30/May/2020 01:25 PM | 0 | 2019-08-13 01:00 | 2019-09-20 18:00 |  | On boarding |  | Beta Release | Bug | SP-I1 | Backlog
SP-I5 | Change the icon images |  | Sample Project | Backlog | Jonus | Jonus | To do | Low | 30/May/2020 01:25 PM | 3 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | Beta Release | Task | SP-I2 | Backlog
SP-I4 | Store it in our database to generate charts on customer likings. |  | Sample Project | Backlog | Martha | Jonus | To do | Medium | 30/May/2020 01:25 PM | 1 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding |  | Beta Release | Bug | SP-I2 | Backlog
SP-I3 | Work on the script |  | Sample Project | Backlog | Martha | Jonus | To do | High | 29/May/2020 01:25 PM | 1 |  |  |  | On boarding | Low,None,Medium | Beta Release | Task | SP-I2 | Backlog
SP-I2 | As a user, I would like to receive weekly mails on the latest appliances on your site. |  | Sample Project | Backlog | Martha | Jonus | To do | Low | 28/Jun/2020 01:25 PM | 8 | 2019-08-13 01:00 | 2019-08-30 18:00 |  | On boarding | High | Beta Release | Story |  | Backlog
SP-I1 | As a user, I prefer to see a how-to video on using the appliance. |  | Sample Project | Backlog | Jonus | Jonus | To do | Medium | 26/May/2020 01:25 PM | 8 | 2019-08-14 01:00 | 2019-08-30 18:00 |  | On boarding | Low | Beta Release | Story |  | Backlog | [{"Comments":"It doesn't needed now.","addedBy":"Jonus"}]